## Sheet1
Electrical Commissioning (Non LEED)
Project:
CPM:
Date(s):
Design
| Constructor | CPM | Professional | Yes | No | Reading | Comments (Attach Reports)
Electrical Service (primary)
Duct bank Mandrel test Report
Manhole installation (attach pictures and report)
Cabling, racking & installation radius
Terminations and Grounding
Confirm Equipment Clearances
Secondary voltage readings
Secure and Clean
Labeling
Electrical Service (MDP)
Installation and housekeeping pad
Grounding and bonding
Phase balance report
Voltage drop
Directory (Spot check accuracy)
Directory has unique descriptions
Clean and secure
GFI Trip adjustment ( Test )
TVSS installation (line distance)
Meter Installation (60" AFF)
Grounding and bonding (Record information)
Ufer connection and electrode conductor size
Bond - building steel, water service, gas line
Ground ring connections
Telecom connections
Special grounding needs and components
Separately derived system grounding conductor
Generator
installation, exhaust and accessibility
Verify grounding and bonding
Cold weather starting and service requirements
Transfer switch connections and operation
Run test results and transfer time
Load test results (Factory or field as specified)
Phase balance report and voltage out-put
Emergency power distribution
Installation of panels
Voltage drop and phase balance report
Power loss test and reaction time
Directories and labeling
Identification of raceways and junction boxes
Warning label on equipment served by normal and "E" power
Clean and secure
Dry type transformers
Installation per NEC (Clearances)
Installation per manufacturers instruction (Clearances)
Vibration and sound isolation
Secondary neutral bond (size, type and location)
Record tap and secondary voltage
Grounding (Record size, method and distance)
Motor Control
Motor control center installation and compliance with specification
MCC voltage drop and phase balance
MCC Test trips and overload devices
VFD Installation and compliance
Voltage drop and phase balance (All systems)
Record all settings, restrictions, fuse sizes and trip adjustments
Label source and load served
Clean and secure
Control wiring and operation
Fire Alarm
Installation and compliance
Remote annunciation (Confirm operation)
Identification of Heads and Addresses
Identification of raceway and J-boxes
Walk test report
Documentation for EOL resistor locations and interface devices
Clean heads at final acceptance
Wiring Devices
Receptacles, rigidly and securely installed (Test every one!)
Receptacle polarity test report
GFCI Testing
Covers and field labeling (see specifications)
Snap switch installation
Barriers for voltage restriction ( over 300 )
Verify field connection and sequence of operation
cover plates and field circuit identification
Lighting system (Interior)
Verify installation and fixture support
Lamps and bi-level switching
"E" egress lighting is not to have secondary overcurrent protection
Verify location and operation of exit signs
Circuit identification
General electrical installation
Fire stopping installed and labels in place
All junction box covers installed
Verify disconnect locations and service receptacles
Confirm required clearances around equipment and access
Raceway is supported as required, not to ductwork or plumbing
Electrical debris removed from above ceilings
All electrical identification complete and proper
Voice/Data Systems
Verify all grounding and bonding
Fire stopping complete and labeled
Cable supports and raceway fill conform to specifications
Spare raceways and pull strings in place
Test reports as required by the specifications
Audio/Video Systems
Isolated ground connection (witness "lift" test)
Document the locations of taps and splitters
Record values of taps and splitters
Produce copies of test reports
Document signal loss and cable lengths
Cabling not to be supported by or attached to other systems
Exterior lighting and power
Verify conductor installation with specification
Verify pole installation and grouting
Confirm secondary overcurrent protection device
Review pole and fixture finish
Verify locations for receptacle and service GFCIs
Circuit identification
Confirm Operation (Test controls)
Document Conductor paths and hand hole locations (dimensions)
Temperature Control
BAS on "E" power
Test FA interface
Document auxiliary device locations
Copies of BAS Contractor's tests
Witness Failsafe operation (Power outage)
Copies of all test reports
Test lighting controls
Document pneumatic interface points
Testing
All test reports filed in the Commissioning Manual
Compare reports received to the requirements (Provide Check List)
All reports must list the witnesses
Training
Fire Alarm
VFD
MCC
Generator
Specialty equipment
Spare Parts (see specifications)
Fuses and fuse cabinet
Specialized tools
Lamps/ballasts
Breakers
Devices/wire