## Sheet1
Mechanical Commissioning (Non LEED)
Project:
CPM:
Design
| Constructor | CPM | Professional | Yes | No | Reading | Comments
Plumbing
Domestic water installation
Domestic water piping installed according to plans
Domestic water system isolation valves installed per plans and specifications
Hot water heater piped per design details
Softener system piped per design details
All equipment has isolation valves for servicing
Domestic water functional
Adequate water pressure at farthest fixture during high load
Hot water heater temperature output matches design
Hot water temperature maintained at high load
Hot water recirculating pump functioning
Hot water temperature maintained at all recirculated locations
Hot water faucet mixing valves operating properly
Flush valves operate properly
Test water hardness to confirm softener functioning properly
Gas piping installation
Gas piping installed according to plans
Piping system isolation valves installed per plans and specifications
All equipment has isolation valves for servicing
Sewer system installation
Piping installed according to plan
cleanouts installed per plan and in accessible locations
Floor drains installed according to plans
Piping material installed as specified
HVAC
Steam system installation
Piping installed per plans
Valves, strainers and similar are steel on HPS system to past the relief valve
pressure reducing stations installed per plans
All equipment has isolation valves for servicing
Steam system functional
Steam pressures per plan
De-superheater functioning and producing requires steam temperature
Hot water heating system installation
Heating water piping installed according to plans
Heating water isolation valves installed per plans and specifications
Hot water pumps and accessories installed per plan
Hot water converters installed per plans
All equipment has isolation valve for servicing
Verify expansion tank pressure setting (engineer to provide value)
Hot water heating system functional
Hot water discharge temperatures set per plans
Check piping system for excessive noise levels
Hot water flow and temperature at all coils per plan (TAB report)
Chilled water system installation
Chilled water piping installed according to plans
Chilled water isolation valves installed per plans and specifications
Chilled water pumps and accessories installed per plan
Chiller installed per plans
Well water piping and plate frame installed per plans
All equipment has isolation valves for servicing
Verify expansion tank pressure setting (engineer to provide value)
Chilled water system functional
Chiller discharge temperatures set per plans (maintained at various loads)
Check piping system for excessive noise levels
Chilled water flow and temperature at all coils per plan (TAB report)
Condenser water temperatures per plans
Well water plate frame temperatures per plan (maintained at various loads)
AHU and ductwork installation
AHU installed per plans
Adequate access available to service all coils and motors
Dampers installed per plan and functional (Siemens report)
Exhaust fans installed per plans
Ductwork pressure test performed by contractor
Fire dampers installed at fire walls (when code required)
AHU and ductwork functional
Airflows at AHU and terminal boxes per plans (TAB report)
Exhaust airflows per plans (TAB report)
AHU discharge temperatures per plans (TAB report)
Check ductwork for excessive noise and leaks