## Checklist
PROJECT CLOSEOUT CHECKLIST
C - Constructor |  | D - Design Professional |  |  | P - CPM
Date
| Action Item | [5 empty] | Complete |  | Comments
D | Prepare list of spare parts and materials.
P | Verify parts and materials, received & stored.
C | Provide marked up record documents.
C | Provide initial copy of O & M manual.
C | Prepare initial list of incomplete items and request
final observation.
P | Test and Balance mechanical systems.
P | Review Constructor's record documents and forward
to Design Professional.
CP | Provide startup and O & M training to Owner's staff.
D | Monitor startup and training of all systems and
prepare a report for Owner.
DCP | Conduct the substantial completion observation.
D | Prepare detailed list of incomplete items.
C | Complete work required for list of incomplete items.
D | Record changes to documents on final set of
record documents.
P | Submit Test and Balance report to DP for review.
C | Submit commissioning manual to Owner.
C | Submit warranty manual to Owner.
D | Review and approve test and balance report.
D | Review and approve commissioning and warranty
manuals.
C | Complete list of incomplete items and return list
signed by subcontractor and contractor indicating
all items complete and request final observation.
DCP | Final observation of list of incomplete items.
D | Complete record documents and transmit one
hard copy and one electronic copy for CPM review.
D | Return Constructor's mark ups to the CPM.
D | Submit additional closeout documents as required
by contract including design analysis.
C | Submit final application for payment.
D | Submit final payment request.
D | Prepare a letter recommending acceptance of the
project.
P | Approve final payments.
P | Issue evaluations for Constructor and Design
Professional.
All Items Completed |  |  |  |  | CPM
Approved |  |  |  |  | Associate Director of Design & Construction
PROJECT SUMMARY
CONSTRUCTOR
| Initial Contract Amount |  |  |  |  | $
| Total Amount of Change Orders |  |  |  |  | $
|  |  | Total Construction Cost |  |  | $
[8 empty] | % |  | Rework Required
| Changes Due to User Request |  |  |  | $ |  |  |  | $
| Changes Due to Physical Plant Request |  |  |  | $ |  |  |  | $
| Changes Due to E&O by DP |  |  |  | $ |  |  |  | $
| Changes Due to Unknown Conditions |  |  |  | $ |  |  |  | $
Original Contract Time
Days Added By Change
Proposed Completion Date
Date of Substantial Completion
Date of Final Acceptance
DESIGN PROFESSIONAL
| Original Contract Amount |  |  | $
| Total Amendments |  |  | $
% Change

## Summary
PROJECT SUMMARY
CONTRACTOR
| Initial Contract Amount |  |  | $
| Total Amount of Change Orders |  |  | $
|  | Total Construction Costs |  | $
[5 empty] | % |  | Rework Required
| Changes Due to User Request |  | $ |  |  | $
| Changes Due to PhP Request |  | $ |  |  | $
| Changes Due to E & O by DP |  | $ |  |  | $
| Changes Due to Unknown Conditions |  | $ |  |  | $
Original Contract Time
Days Added By Change
Proposed Completion Date
Date of Substantial Completion
Date of Final Acceptance
CONSULTANT
| Original Contract Amount |  | $
| Total Amendments |  | $
% Change